Week 7 Project Summary

HealthConnect Clinic — Data Analytics Track

AnalystLab Africa Experience Lab — Week 7

Prepared by Oluwatosin Olusanya, Data Analyst — AnalystLab Africa

# 1-2. What I Planned vs. Actually Tested

Planned to independently re-validate every Week 5/6 KPI and statistical test against the raw dataset, and test whether the two headline drivers (lead time, prior no-show history) remain valid when combined and when checked across demographic segments. Completed all of this, plus tested and formally rejected one additional claim (see below) rather than carrying it forward unchecked.

# 3. Most Important Testing Results

- All 8 previously reported KPIs and both chi-square tests reproduced exactly from the raw CSV — the analytical pipeline has no calculation errors.

- Combining lead time and prior history into a single risk matrix identifies a clear, appropriately sized highest-risk segment: 1,529 appointments (1,035 patients) at 63.6% no-show, versus 28.0% for the lowest-risk segment.

- The lead-time effect holds across gender and every age group, but is measurably weaker at the youngest and oldest age bands — a genuine refinement.

# 4. Issues or Weaknesses Identified

One specific claim that reminders were disproportionately assigned to lower-risk patients was tested directly and found false; reminder-send rates are nearly identical (71.6-74.3%) across all four risk segments. This claim came from a draft produced with an external tool and was not something I had verified myself before testing it this week.

# 5-6. Improvements Made and Retesting

Added the combined risk-segment matrix as new analysis (not present in Week 5/6), refined the lead-time finding to note its age-dependence, and removed the unsupported reminder-bias claim from the final findings rather than including it. No retest was needed for the rejected claim itself rejecting it based on direct evidence is the correct outcome, not a defect requiring a fix.

# 7-9. Cross-Track Collaboration

Shared the combined risk-segment matrix and the confirmed absence of reminder-assignment bias with the Project Management track, giving them a concrete, sized target group (1,529 appointments) to reflect in Week 8 readiness planning rather than an abstract statistical pattern.

# 10. Key Findings / Validation Outcomes

The core Week 5/6 analytics are fully validated and reproducible. The project now has both an individual-driver view (lead time, history) and a combined, actionable risk-segmentation view ready for final integration.

# 11. Major Challenges

The main challenge was evaluating a draft analysis document that mixed genuine, verifiable findings with claims describing tooling (SQL, SPSS, an interactive dashboard) that was never actually part of this project. Resolving this required verifying every specific number against the raw data before including anything, and explicitly deciding to exclude the fabricated dashboard-testing narrative rather than adapt it.

# 12. Important Decisions Made

Decided to test the reminder-assignment-bias claim explicitly rather than assume it was true, and to document its rejection transparently in the Testing & Validation Record rather than quietly dropping it. This reflects the assignment's own instruction to document genuine validation rather than invent issues — the same principle applies to not inventing findings that don't hold up.

# 13-14. Remaining Limitations and Issues

- This remains descriptive/associational validation, not causal.

- No interactive dashboard exists for this project; all visuals are static charts, consistent with the tooling used since Week 5.

- The age-group refinement is based on modest sample sizes once segmented; direction is clear, exact magnitude is indicative.

# 15. Contribution to the Overall HealthConnect Project

Provided the Project Management track with a validated, appropriately sized highest-risk patient segment for Week 8 planning, and confirmed the underlying analytics have no errors — giving the wider project a trustworthy foundation for final integration and presentation.

# 16. What Must Be Completed Before Week 8

Confirm with the Data Science and Project Management tracks that this week's combined risk-segment findings have been incorporated into their own final outputs, and prepare the final presentation narrative connecting the Data Analytics findings to the Data Science predictive model.